## Slide 1: City of Austin Watershed Protection Department CIP Project design/implementation
March 27, 2014
Notes: Thank you for the opportunity to show the committee what the Watershed Protection Department has been able to accomplish with the 2006 bond funding and for what could be accomplished with future funding.

## Slide 2: Steps of a CIP Project
Identify
Verify
Prioritize
Analyze
Design
Permit
Project Manual
Construction Oversight

## Slide 3: Identify: Locating the problem
Goal: Reduce flood hazards to citizens of Austin

## Slide 4
Sometimes the flooding is away from the creeks due to undersized storm systems or failed storm pipes

## Slide 5: Identify: Locating the problem
WPD master plan
Floodplain maps
Drainage complaints
StormCAD models
Annexation reviews
Infrastructure Assessment

## Slide 6: Verify: Define the problem
Field Visit
Survey
Post-storm investigations
Model development
TV inspections

## Slide 8
Localized Flood Hazard Mitigation Program
FOD Field Engineering
FOD Pipe Condition Assessment
Rehabilitation & Construction
Inspection and Cleaning
Partnership Opportunities
Inlet: > 32,000
Manhole: > 4,000
Outfall: >5,000
Storm Drain System: ~1000 mi.

## Slide 9: Master Plan Objectives
Develop Flood Scores* for 28 Watersheds with:
Updated, Current Resources
Revised, Streamlined Methodology
* Flood Score: A “first cut” estimation of potential flooding severity for structures and street crossings due to creek bank overtopping. These scores will be used to identify the need for improvement projects and prioritize project areas based on their relative scores.

## Slide 10: Master Plan Objectives
Capital Improvement Projects: Identifying Priorities
  Flood scores
  Feasibility Assessments
  Multi-mission objectives
  Cost
  Access
  Impact to citizens
  Evaluate projects ranging in scale from a roadway crossing improvement to regional detention ponds

## Slide 11: Analyze: Define the solution
Raise roadways
Improve stormwater conveyance under roadways with culverts or bridges
Regional detention ponds
Property buyouts
Channel conveyance modifications
Channel diversions
Storm drain repair/replace
Storm drain conveyance improvements
Green stormwater infrastructure

## Slide 12: Analyze: Model Development

## Slide 13: Analyze: Preliminary Engineering
Contents:
  Site Investigation
  Survey
  Model development/review
  Utility Assessment
  Impact to WPD mission
  Impact to COA mission
  Alternatives analysis
  Cost estimate
  Recommendation
Team
  WPD Engineer (P.E.)
  WPD Engineer (EIT)
  Mission Integration Reps

## Slide 14: Analyze: Preliminary Engineering
Identify all scope items including:
Flooding – no adverse impact
Erosion – improve /no adverse impact
Water quality – improve/no adverse impact
Use of privately owned land – easements
Use of publicly owned land – utilities
Connectivity – roadway, bike/pedestrian pathway
Neighborhood plan

## Slide 15: Design: Construction Plan Set
Contents:
  Drainage Maps
  Erosion/Sedimentation Plan
  Traffic Control
  Site Plan View
  Cross-Sections
  Landscape Plan
  Structural Details
Team:
  Project Engineer
  Project Manager (COA)
  Drainage Engineer
  Geotechnical Engineer
  Structural Engineer
  Landscape Architect
  CAD Designer
  Surveyor

## Slide 16: Design: Construction Plan Set
WPD Engineer Role

## Slide 17: Design: Permit
Reviewed for:
  Compliance with code and criteria
    Land development code
    Drainage criteria manual
    Environmental criteria manual
    Transportation criteria manual
  Appropriate access/easement
  No adverse impact
Role of the WPD Engineer:
  Set up the project prior to permitting
  Conduit of information between PM, consultant, and reviewer

## Slide 18: Design: Project Manual
What is the purpose of a project manual?
  Provides a narrative to the plan set
  Describes the materials and methods of construction
  Quantifies items for a bid
Contents
  Bidding requirements
  Contract forms
  Summary of work
  Geotechnical report
  Bid items
  COA standard technical specifications
  Special provisions
  Special specifications
  Stormwater pollution prevention plan

## Slide 19: Construction: Implementing Design
Team
  COA Project Manager
  WPD Project Engineer
  Consultant Project Engineer
  Contractor Superintendent
  COA Construction Inspector
  COA Environmental Inspector
Role of WPD Engineer:
  Weekly construction meetings
  Provide information to residents
  Review change orders

## Slide 20: Parkway Channel Improvement and Stream Stabilization
CIP ID No. 5789.087
Final Completion June 2012

## Slide 21: WPD Mission Goals
Flood Control
Increased capacity of infrastructure from Parkway Drive to Shoal Creek, replaced failing masonry wall channel with ~ 175-ft of 4x4 box culvert
Erosion Control
Stabilized culvert outlet and 170-ft of eroded creek bank with combination of MSE walls, soil lifts, vegetation, armored transitions
Riparian Restoration
Removed invasive plants from creek bank and private property and replaced with natives and adapted natives.
Field Operations
Provided permanent access to Shoal Creek down to the N. Lamar culvert system

## Slide 22: Before & After

## Slide 23: Before & After

## Slide 24: Before & After

## Slide 25: Construction
January 2012: Excavating & forming the junction box

## Slide 26: Construction
February/March 2012: Excavating & placing precast box culverts, 1501 Parkway driveway

## Slide 27: Construction
April 2012: Forming cast-in-place culvert, MSE wall

## Slide 28: Construction
April/May 2012: MSE wall

## Slide 29: Construction
June 2012: Vegetation

## Slide 30: Schedule
Preliminary Phase: 2007-2009
  Acquired funding
Design Phase: January 2009 – July 2011 (2 1/2 YR)
  30% June 2009
  60% August 2009
  90% July 2010
    Additional easement & scope
    Scope revision between Sept. 2009-March 2010
    Extension of bank stabilization, additional landscaping
  Permitting September 2010 – April 2011
  Project Manual Finalized May 2011-June 2011
Bid Phase: July 2011 – November 2011 (5 months)
  1 rebid
Construction Phase: December 2011-June 2012 (7 months)

## Slide 31: Public Private Partnership (P3) South Shore Storm Drain Improvements
Project# 5789.100
Final Completion December 2012

## Slide 32: Proposed Private Development

## Slide 33: Current View of Development

## Slide 34: Approximate alignment of existing 36” pipe (from South Lakeshore)

## Slide 35: Approximate alignment of existing 36” pipe (from outfall)
Existing 36” Pipe

## Slide 36: The existing 36” pipe crosses through a memorial tree grove with protected and heritage class trees in the nearby areas.

## Slide 37: Approximate alignment of proposed 60” pipe (from South Lakeshore)

## Slide 38: Planning Needed Beyond Project

## Slide 39: Development Engineer

## Slide 40: City Design

## Slide 41: City Design

## Slide 42: Project Details
Location
South Shore PUD – Lake Shore Blvd. & Town Creek Dr.
Opportunity
Partner with a developer to upgrade an underperforming storm drain in a re-developing area
Cost Participation & Reimbursement project
Developer was supplied with $33,000 in pipe material and reimbursed $440,000 for design and construction of storm drain improvements.
Cost Effectiveness
Saved $1.28-million compared to constructing projects alone without partnership

## Slide 43: South Shore Storm Drain Improvements Project# 5789.100

## Slide 44: Bonus Feature – New Photo Opportunity with Austin Skyline in the Background